## Overview
BestoClinic — User Acceptance Testing (UAT)
Project | BestoClinic Multi-Tenant Clinic Management Platform
Version | April 2026 Release
UAT Period | April 23 – 25, 2026 (3 days)
Deadline | Saturday, April 25, 2026
Prepared By | Claude Code (AI-assisted)
Date Prepared | April 23, 2026
TEST ENVIRONMENT
Backend URL | http://192.168.1.60:5001/api/v1
Website URL | http://localhost:5173 (Vite dev)
Mobile App | React Native 0.76.9 (Android emulator / physical device)
Database | MongoDB (multi-tenant, per-clinic DBs)
CREDENTIAL SUMMARY
Clinic | Jathar Clinic ¦ Code: JATHR4521
Role | Email | Password | Notes
SuperAdmin / Owner | dr.sandeep@jathardental.in | Doctor@2025 | Full access to all features
Admin | vishal@jathardental.in | Staff@2025 | Clinic admin (no platform)
Doctor | dr.priya@jathardental.in | Doctor@2025 | Clinical features only
Receptionist | snehal@jathardental.in | Staff@2025 | Front desk features
Guardian 1 | harshadadaml6@example.com | Staff@2025 | Patient with dependents
Guardian 2 | jyotikulkarn97@example.com | Staff@2025 | Patient with dependents
Guardian 3 | kavitabhosal15@example.com | Staff@2025 | Patient with dependents
SHEET INDEX
Sheet Name | Scope | Test Case Count (approx)
Owner / SuperAdmin | All tenant management pages + analytics (website) | ~90
Doctor | Doctor dashboard, consultations, schedule (website + mobile) | ~85
Receptionist | Front desk, queue, billing (website) | ~45
Billing Officer | Invoices, payments, insurance (website) | ~35
Accountant | Financial reports, invoices (website) | ~25
HR Manager | Staff, payroll (website) | ~20
IT Support | Integrations, settings (website) | ~15
Support Staff | Appointments, reminders (website) | ~15
Patient (Web) | Patient portal website | ~55
Patient (Mobile) | Patient mobile app screens | ~65
Doctor (Mobile) | Doctor mobile app screens | ~55
Auth & Discovery | Login, registration, clinic browsing (web + mobile) | ~40
Platform Admin | Platform-level tenant/plan management (website) | ~50
Push & Real-Time | FCM push notifications, socket events, telemedicine | ~40
Backend & APIs | API contracts, background jobs, middleware | ~50
STATUS LEGEND
Not Tested | Test not yet executed
Pass | Feature works as expected
Fail | Feature broken — log Bug ID
Blocked | Cannot test (dependency, environment issue)
Partial | Some sub-steps pass, others fail
PRIORITY LEGEND
P0 - Critical | Blocker — must fix before release (auth, data loss, crash)
P1 - High | Major feature broken — core workflow affected
P2 - Medium | Feature works but has issues — usability, minor bugs
P3 - Low | Cosmetic, nice-to-have, edge cases

## Owner - SuperAdmin
TC # | Module / Page | Platform | Feature / Test Case | Steps to Reproduce | Expected Result | Priority | Status | Tested By | Test Date | Bug ID / Notes
DASHBOARD
TC-001 | Dashboard | Web | Dashboard loads with stats cards | Login as owner → navigate to /clinic | Shows totalPatients, todayAppointments, pendingInvoices, revenueThisMonth | P0 - Critical | Not Tested
TC-002 | Dashboard | Web | Revenue chart renders | View dashboard → check revenue chart section | Monthly revenue chart renders with correct data points | P1 - High | Not Tested
TC-003 | Dashboard | Web | Today's appointments list | View dashboard → scroll to appointments section | Shows today's scheduled appointments with patient names, times, status | P1 - High | Not Tested
TC-004 | Dashboard | Web | Doctor leaderboard | View dashboard → scroll to leaderboard | Shows doctors ranked by appointments/revenue for current period | P2 - Medium | Not Tested
TC-005 | Dashboard | Web | Live queue monitor | View dashboard → check queue section | Shows current patients in queue with status and wait time | P1 - High | Not Tested
TC-006 | Dashboard | Web | Alerts / notifications panel | View dashboard → check alerts section | Shows recent alerts (overdue invoices, low stock, expiring insurance) | P2 - Medium | Not Tested
BRANCH MANAGEMENT
TC-007 | Branches | Web | List all branches | Navigate to /clinic/branches | Shows all clinic branches with name, address, status | P1 - High | Not Tested
TC-008 | Branches | Web | Create new branch | Click "Add Branch" → fill form → submit | New branch created and appears in list | P1 - High | Not Tested
TC-009 | Branches | Web | Edit branch details | Click on a branch → edit fields → save | Branch details updated successfully | P2 - Medium | Not Tested
TC-010 | Branches | Web | Assign staff to branch | Edit branch → assign staff members | Staff assigned and visible under branch | P2 - Medium | Not Tested
DEPARTMENT MANAGEMENT
TC-011 | Departments | Web | List all departments | Navigate to /clinic/departments | Shows all departments with name, head, doctor count | P1 - High | Not Tested
TC-012 | Departments | Web | Create department | Click "Add Department" → fill name, head → submit | New department appears in list | P1 - High | Not Tested
TC-013 | Departments | Web | Assign doctors to department | Edit department → add doctors | Doctors appear under department | P2 - Medium | Not Tested
DOCTOR MANAGEMENT
TC-014 | Doctors | Web | List all doctors | Navigate to /clinic/doctors | Paginated list of all doctors with qualifications, status | P1 - High | Not Tested
TC-015 | Doctors | Web | View doctor profile | Click on a doctor from list | Full profile: specialization, schedule, documents | P1 - High | Not Tested
TC-016 | Doctors | Web | Edit doctor details | Edit doctor → change fields → save | Doctor details updated | P2 - Medium | Not Tested
TC-017 | Doctors | Web | Manage doctor availability | Navigate to doctor availability page | View/edit doctor schedule slots | P1 - High | Not Tested
STAFF MANAGEMENT
TC-018 | Staff | Web | List all staff | Navigate to /clinic/staff | Shows non-doctor staff with roles, department, status | P1 - High | Not Tested
TC-019 | Staff | Web | Create staff member | Click "Add Staff" → fill form (name, email, role) → submit | New staff created with correct role permissions | P1 - High | Not Tested
TC-020 | Staff | Web | Edit staff role/permissions | Edit staff → change role → save | Role updated and permissions reflect correctly | P1 - High | Not Tested
TC-021 | Staff | Web | Deactivate staff | Click deactivate on a staff member | Staff soft-deleted, cannot login | P2 - Medium | Not Tested
PATIENT MANAGEMENT
TC-022 | Patients | Web | List all patients | Navigate to /clinic/patients | Paginated list with search, patientId, name, phone | P1 - High | Not Tested
TC-023 | Patients | Web | Search patient by name/ID | Type in search box | Filtered results matching query | P1 - High | Not Tested
TC-024 | Patients | Web | View patient profile | Click on a patient | Full profile: demographics, medical history, contact | P1 - High | Not Tested
TC-025 | Patients | Web | Create patient | Click "Add Patient" → fill form → submit | Patient created with auto-generated patientId | P1 - High | Not Tested
TC-026 | Patients | Web | Edit patient details | Edit patient → modify fields → save | Patient details updated | P2 - Medium | Not Tested
TC-027 | Patients | Web | Soft-delete patient | Click delete on patient → confirm | Patient soft-deleted (deletedAt set), disappears from list | P2 - Medium | Not Tested
TC-028 | Patients | Web | Bulk import patients (CSV) | Click bulk upload → upload CSV → submit | All valid rows created, errors reported for invalid rows | P2 - Medium | Not Tested
APPOINTMENTS (ADMIN VIEW)
TC-029 | Appointments | Web | List appointments with filters | Navigate to /clinic/appointments → use filters | Appointments filtered by doctor, branch, status, date range | P0 - Critical | Not Tested
TC-030 | Appointments | Web | Calendar view — Week | Switch to Calendar view → Week mode | Week calendar renders with time slots and events | P0 - Critical | Not Tested
TC-031 | Appointments | Web | Calendar view — Month | Switch to Calendar view → Month mode | Month grid renders with appointment dots/counts | P1 - High | Not Tested
TC-032 | Appointments | Web | Calendar view — Day | Switch to Calendar view → Day mode | Single day timeline with all appointments | P1 - High | Not Tested
TC-033 | Appointments | Web | Calendar view — Agenda | Switch to Calendar view → Agenda mode | Agenda list view with date range | P1 - High | Not Tested
TC-034 | Appointments | Web | List view with pagination | Switch to List view → paginate | Paginated table with appointment details | P1 - High | Not Tested
TC-035 | Appointments | Web | Timeline view | Switch to Timeline view | Horizontal timeline of appointments grouped by doctor | P2 - Medium | Not Tested
TC-036 | Appointments | Web | Board view (Kanban) | Switch to Board view | Columns by status (requested, confirmed, checked_in, etc.) | P2 - Medium | Not Tested
TC-037 | Appointments | Web | Tile view (cards) | Switch to Tile view | Card-based layout with appointment summaries | P2 - Medium | Not Tested
TC-038 | Appointments | Web | Create appointment | Click "New Appointment" → fill patient, doctor, date, time → submit | Appointment created with status=requested | P0 - Critical | Not Tested
TC-039 | Appointments | Web | Update appointment status | Click appointment → change status (confirm, check-in, etc.) | Status transitions follow: requested→confirmed→checked_in→in_progress→completed | P0 - Critical | Not Tested
TC-040 | Appointments | Web | Cancel appointment | Click cancel on appointment → provide reason | Appointment marked cancelled, cancel reason saved | P1 - High | Not Tested
TC-041 | Appointments | Web | Click on calendar slot to create | Click empty slot on calendar | Opens create form pre-filled with selected date/time | P2 - Medium | Not Tested
QUEUE MANAGEMENT
TC-042 | Queue | Web | View live queue | Navigate to /clinic/queue | Shows current patient queue with positions, status, wait times | P1 - High | Not Tested
TC-043 | Queue | Web | Call next patient | Click "Call Next" button | Next patient called, status updated | P1 - High | Not Tested
TC-044 | Queue | Web | Assign room | Select a queue entry → assign room | Room assignment saved and visible | P2 - Medium | Not Tested
PRESCRIPTIONS
TC-045 | Prescriptions | Web | List all prescriptions | Navigate to /clinic/prescriptions | All prescriptions with patient, doctor, date, status | P1 - High | Not Tested
TC-046 | Prescriptions | Web | View prescription details | Click on a prescription | Full details: medicines, dosage, frequency, notes | P1 - High | Not Tested
BILLING (ADMIN)
TC-047 | Billing | Web | View invoice list | Navigate to /clinic/billing | All invoices with status, amounts, dates | P0 - Critical | Not Tested
TC-048 | Billing | Web | Create invoice | Click "Create Invoice" → add line items → submit | Invoice created with correct totals, tax calculations | P0 - Critical | Not Tested
TC-049 | Billing | Web | Record payment against invoice | Open invoice → click "Record Payment" → enter amount | Payment recorded, invoice status updated (paid/partially_paid) | P0 - Critical | Not Tested
TC-050 | Billing | Web | Write-off invoice | Open overdue invoice → click write-off | Invoice marked as written off | P2 - Medium | Not Tested
INSURANCE MANAGEMENT
TC-051 | Insurance | Web | List insurance providers | Navigate to /clinic/insurance | All insurance companies with plans, contact info | P1 - High | Not Tested
TC-052 | Insurance | Web | Create insurance claim | Click "New Claim" → fill form → submit | Claim created with correct patient/provider link | P1 - High | Not Tested
TC-053 | Insurance | Web | Track claim status | View claim → check status updates | Status reflects: submitted→under_review→approved/rejected | P1 - High | Not Tested
INVENTORY
TC-054 | Inventory | Web | List inventory items | Navigate to /clinic/inventory | All items with stock levels, expiry dates, reorder points | P1 - High | Not Tested
TC-055 | Inventory | Web | Low stock alerts | Check items below reorder point | Low stock items highlighted with alert indicator | P1 - High | Not Tested
TC-056 | Inventory | Web | Restock item | Select item → restock → enter quantity | Stock level updated, transaction logged | P2 - Medium | Not Tested
TC-057 | Inventory | Web | Expiry tracking | View expiring items section | Items expiring within threshold highlighted | P2 - Medium | Not Tested
PROCEDURES
TC-058 | Procedures | Web | List procedure templates | Navigate to /clinic/procedures | All procedures with name, cost, duration, required materials | P1 - High | Not Tested
TC-059 | Procedures | Web | Create procedure template | Click "Add Procedure" → fill form → submit | Procedure template created | P2 - Medium | Not Tested
TC-060 | Procedures | Web | Check inventory availability for procedure | Select procedure → check availability | Shows if all required materials are in stock | P2 - Medium | Not Tested
ANALYTICS & REPORTS
TC-061 | Analytics | Web | Analytics dashboard loads | Navigate to /clinic/analytics | Dashboard shows KPIs, revenue trends, appointment charts | P1 - High | Not Tested
TC-062 | Analytics | Web | Revenue analytics | Navigate to /clinic/revenue | Revenue by branch, by doctor, monthly trend, outstanding aging | P1 - High | Not Tested
TC-063 | Analytics | Web | Revenue by branch chart | View revenue analytics → branch breakdown | Bar chart with branch revenue data | P2 - Medium | Not Tested
TC-064 | Analytics | Web | Doctor performance metrics | View analytics → doctor tab | Table with doctorName, totalAppointments, noShowCount, revenue | P2 - Medium | Not Tested
TC-065 | Analytics | Web | Outstanding aging analysis | View billing analytics → outstanding tab | Aging buckets: 0-30, 31-60, 61-90, 90+ days | P2 - Medium | Not Tested
TC-066 | Reports | Web | Generate custom report | Navigate to /clinic/reports → configure → generate | Report generated with selected filters and exported | P2 - Medium | Not Tested
TC-067 | Compliance | Web | Compliance dashboard | Navigate to /clinic/compliance | Care compliance rates, consent tracking, audit trail | P2 - Medium | Not Tested
TELEMEDICINE (ADMIN VIEW)
TC-068 | Telemedicine | Web | List telemedicine sessions | Navigate to /clinic/telemedicine | All sessions with status, participants, timestamps | P1 - High | Not Tested
TC-069 | Telemedicine | Web | View session details | Click on a session | Full session: video status, chat messages, files shared | P2 - Medium | Not Tested
SETTINGS & CONFIGURATION
TC-070 | Settings | Web | Clinic settings page loads | Navigate to /clinic/settings | Shows clinic name, logo, address, working hours | P1 - High | Not Tested
TC-071 | Settings | Web | Update clinic name/logo | Edit clinic name → save | Clinic name updated across all pages | P2 - Medium | Not Tested
TC-072 | Settings | Web | Manage working hours | Edit working hours → save | Working hours reflected in availability | P2 - Medium | Not Tested
TC-073 | Notifications | Web | Notification settings | Navigate to /clinic/notifications | Notification templates, delivery logs | P2 - Medium | Not Tested
TC-074 | Integrations | Web | View active integrations | Navigate to /clinic/integrations | Shows integration status (SMS, email, payment gateways) | P2 - Medium | Not Tested
TC-075 | QR Code | Web | Generate QR code | Navigate to /clinic/qr-code → generate | QR code generated for patient check-in | P3 - Low | Not Tested
TC-076 | Branch Monitor | Web | Real-time branch metrics | Navigate to /clinic/branch-monitor | Shows capacity, presence, room availability per branch | P2 - Medium | Not Tested
PAYROLL
TC-077 | Payroll | Web | View payroll overview | Navigate to /clinic/payroll | Staff salary list, cycle status | P2 - Medium | Not Tested
CONSULTATIONS
TC-078 | Consultations | Web | List all consultations | Navigate to /clinic/consultations | All treatment records with patient, doctor, date, status | P1 - High | Not Tested

## Doctor (Web)
TC # | Module / Page | Platform | Feature / Test Case | Steps to Reproduce | Expected Result | Priority | Status | Tested By | Test Date | Bug ID / Notes
DOCTOR DASHBOARD
TC-001 | Dashboard | Web | Dashboard loads with greeting + stats | Login as doctor → navigate to /clinic/doctor-dashboard | Shows greeting, stats (appointments, revenue, patients), current room badge | P0 - Critical | Not Tested
TC-002 | Dashboard | Web | Today's schedule timeline | View dashboard → check schedule section | Shows today's appointments in timeline format | P1 - High | Not Tested
TC-003 | Dashboard | Web | Live queue display | View dashboard → check queue section | Shows patients waiting for this doctor | P1 - High | Not Tested
TC-004 | Dashboard | Web | Compliance metrics | View dashboard → compliance section | Shows care compliance rates, pending reminders | P2 - Medium | Not Tested
TC-005 | Dashboard | Web | Week total appointments stat | Check stats cards on dashboard | weekTotal field shows appointments for current week | P2 - Medium | Not Tested
MY APPOINTMENTS
TC-006 | Appointments | Web | List doctor's appointments | Navigate to /clinic/doctor-appointments | Shows only this doctor's appointments (filtered by userId) | P0 - Critical | Not Tested
TC-007 | Appointments | Web | Calendar view — Week | Switch to Calendar → Week mode | Week calendar with doctor's appointments | P0 - Critical | Not Tested
TC-008 | Appointments | Web | Calendar view — Month | Switch to Calendar → Month mode | Month view with appointment indicators | P1 - High | Not Tested
TC-009 | Appointments | Web | Calendar view — Day | Switch to Calendar → Day mode | Single day view with time slots | P1 - High | Not Tested
TC-010 | Appointments | Web | Filter by status | Use status filter dropdown | Appointments filtered correctly | P1 - High | Not Tested
TC-011 | Appointments | Web | Confirm appointment | Find requested appointment → click confirm | Status changes to confirmed | P0 - Critical | Not Tested
TC-012 | Appointments | Web | Start consultation from appointment | Click "Start Consultation" on checked-in appointment | Opens consultation room, appointment status→in_progress | P0 - Critical | Not Tested
CONSULTATION ROOM
TC-013 | Consultation | Web | Consultation room loads | Click "Start Consultation" on an appointment | Full consultation interface: patient info, notes area, vital signs | P0 - Critical | Not Tested
TC-014 | Consultation | Web | Add clinical notes | Type in chief complaint + examination notes → save | Notes saved to treatment record | P0 - Critical | Not Tested
TC-015 | Consultation | Web | Record vital signs | Enter BP, heart rate, temperature, etc. | Vital signs recorded on treatment record | P1 - High | Not Tested
TC-016 | Consultation | Web | Create prescription during consultation | Click "Add Prescription" → select medicines, dosage → save | Prescription created and linked to consultation | P0 - Critical | Not Tested
TC-017 | Consultation | Web | Upload document/attachment | Click "Upload" → select file | File uploaded and attached to treatment record | P1 - High | Not Tested
TC-018 | Consultation | Web | Complete consultation | Click "Complete" → confirm | TreatmentRecord marked complete, appointment status→completed | P0 - Critical | Not Tested
TC-019 | Consultation | Web | Schedule follow-up from consultation | Click "Schedule Follow-up" → pick date/time | Follow-up appointment created with type=follow_up | P1 - High | Not Tested
TC-020 | Consultation | Web | Send care reminder from consultation | Set up care reminder for patient | Care reminder created and scheduled | P2 - Medium | Not Tested
MY PATIENTS
TC-021 | Patients | Web | List doctor's patients | Navigate to /clinic/doctor-patients | Shows patients this doctor has treated | P1 - High | Not Tested
TC-022 | Patients | Web | View patient records | Navigate to /clinic/doctor-patient-records | Full medical records, treatment history, diagnostics | P1 - High | Not Tested
MY SCHEDULE
TC-023 | Schedule | Web | View own schedule | Navigate to /clinic/doctor-schedule | Shows availability calendar with slots | P1 - High | Not Tested
TC-024 | Schedule | Web | Set availability slots | Edit schedule → define working hours | Slots saved and reflected in booking system | P1 - High | Not Tested
TC-025 | Schedule | Web | Block time slots | Select time range → block | Blocked slots not available for booking | P2 - Medium | Not Tested
VIRTUAL CARE / TELEMEDICINE
TC-026 | Virtual Care | Web | List scheduled teleconsults | Navigate to /clinic/doctor-virtual-care | Shows upcoming video call sessions | P1 - High | Not Tested
TC-027 | Telemedicine | Web | Join video call | Click "Join" on a session | Video call interface opens with WebRTC stream | P0 - Critical | Not Tested
TC-028 | Telemedicine | Web | In-call chat messaging | During video call → send chat message | Message delivered to patient in real-time | P1 - High | Not Tested
EMERGENCY
TC-029 | Emergency | Web | View emergency queue | Navigate to /clinic/doctor-emergency | Shows pending emergency requests with patient info, triage | P0 - Critical | Not Tested
TC-030 | Emergency | Web | Accept emergency request | Click "Accept" on emergency request | Session accepted, video session auto-created | P0 - Critical | Not Tested
TC-031 | Emergency | Web | Decline emergency request | Click "Decline" on emergency request | Request remains for other doctors, does not change session status | P1 - High | Not Tested
NOTIFICATIONS
TC-032 | Notifications | Web | View notifications inbox | Navigate to /clinic/doctor-notifications | Shows all doctor notifications (appointments, reminders, messages) | P1 - High | Not Tested
TC-033 | Notifications | Web | Mark notification as read | Click on notification → mark read | Notification marked read, unread count decreases | P2 - Medium | Not Tested

## Receptionist
TC # | Module / Page | Platform | Feature / Test Case | Steps to Reproduce | Expected Result | Priority | Status | Tested By | Test Date | Bug ID / Notes
RECEPTIONIST DASHBOARD
TC-001 | Dashboard | Web | Dashboard loads | Login as receptionist → /clinic/receptionist-dashboard | Shows greeting, stats (appointments, waiting, revenue), emergency badges | P0 - Critical | Not Tested
TC-002 | Dashboard | Web | Emergency alert badges | Check for emergency requests | Active emergency count visible with badge | P1 - High | Not Tested
TC-003 | Dashboard | Web | Doctor presence board | View presence section | Shows which doctors are online/offline/in-consultation | P1 - High | Not Tested
TC-004 | Dashboard | Web | Quick actions panel | Check quick action buttons | Shortcuts to book appointment, check-in patient, create invoice | P2 - Medium | Not Tested
TC-005 | Dashboard | Web | Daily timeline | View timeline section | Chronological list of today's events | P2 - Medium | Not Tested
APPOINTMENTS
TC-006 | Appointments | Web | List appointments | Navigate to /clinic/receptionist-appointments | Today's and upcoming appointments with patient/doctor info | P0 - Critical | Not Tested
TC-007 | Appointments | Web | Book new appointment | Click "Book" → select patient, doctor, time → submit | Appointment created successfully | P0 - Critical | Not Tested
TC-008 | Appointments | Web | Reschedule appointment | Click appointment → reschedule → pick new time | Appointment rescheduled, old slot freed | P1 - High | Not Tested
TC-009 | Appointments | Web | Cancel appointment | Click cancel → provide reason | Appointment cancelled with reason | P1 - High | Not Tested
TC-010 | Appointments | Web | Check-in patient | Find confirmed appointment → click check-in | Status: confirmed→checked_in, patient added to queue | P0 - Critical | Not Tested
PATIENT MANAGEMENT
TC-011 | Patients | Web | Search patient | Navigate to /clinic/receptionist-patients → search | Find patient by name, ID, or phone | P0 - Critical | Not Tested
TC-012 | Patients | Web | Register walk-in patient | Click "Add Patient" → fill quick form | New patient registered with patientId | P1 - High | Not Tested
TC-013 | Patients | Web | Verify insurance | View patient → check insurance section | Insurance provider and plan visible | P2 - Medium | Not Tested
QUEUE MANAGEMENT
TC-014 | Queue | Web | View live queue | Navigate to /clinic/receptionist-queue | Current queue with positions, wait times, room assignments | P0 - Critical | Not Tested
TC-015 | Queue | Web | Call next patient | Click "Call Next" | Next patient called, display updated | P1 - High | Not Tested
TC-016 | Queue | Web | Assign consultation room | Select queue entry → assign room | Room assigned to patient | P2 - Medium | Not Tested
TC-017 | Queue | Web | Mark queue entry complete | Click complete on a served patient | Entry removed from active queue | P2 - Medium | Not Tested
BILLING AT CHECKOUT
TC-018 | Billing | Web | Generate invoice at checkout | Navigate to /clinic/receptionist-billing → select patient | Invoice created with consultation charges | P0 - Critical | Not Tested
TC-019 | Billing | Web | Process payment | Select payment method → enter amount → submit | Payment recorded, receipt available | P0 - Critical | Not Tested
TC-020 | Billing | Web | Print receipt | Click "Print Receipt" | Receipt generated for download/print | P2 - Medium | Not Tested
NOTIFICATIONS
TC-021 | Notifications | Web | View notifications | Navigate to /clinic/receptionist-notifications | Shows new bookings, cancellations, emergency alerts | P1 - High | Not Tested

## Billing Officer
TC # | Module / Page | Platform | Feature / Test Case | Steps to Reproduce | Expected Result | Priority | Status | Tested By | Test Date | Bug ID / Notes
BILLING OFFICER DASHBOARD
TC-001 | Dashboard | Web | Dashboard loads with stats | Login as billing officer → /clinic/billing-officer-dashboard | Shows greeting, totalInvoiced, totalCollected, totalOutstanding stats | P0 - Critical | Not Tested
TC-002 | Dashboard | Web | Payment collection trends chart | View dashboard → trend chart | Monthly payment collection trend renders | P1 - High | Not Tested
TC-003 | Dashboard | Web | Aging analysis chart | View dashboard → aging chart | Shows 0-30, 31-60, 61-90, 90+ aging buckets | P1 - High | Not Tested
INVOICES
TC-004 | Invoices | Web | List all invoices | Navigate to /clinic/billing-officer-invoices | Paginated invoice list with status, amounts, dates | P0 - Critical | Not Tested
TC-005 | Invoices | Web | Create invoice | Click "Create Invoice" → add patient, line items → submit | Invoice created with correct calculations | P0 - Critical | Not Tested
TC-006 | Invoices | Web | Send invoice to patient | Click "Send" on invoice | Invoice sent (email/notification) | P1 - High | Not Tested
TC-007 | Invoices | Web | Filter invoices by status | Use status filter (draft, sent, paid, overdue) | Invoices filtered correctly | P1 - High | Not Tested
TC-008 | Invoices | Web | View invoice PDF | Click "Download PDF" | PDF generated with correct invoice layout | P2 - Medium | Not Tested
PAYMENTS
TC-009 | Payments | Web | List payments | Navigate to /clinic/billing-officer-payments | All payments with invoice reference, amount, method, date | P0 - Critical | Not Tested
TC-010 | Payments | Web | Record manual payment | Click "Record Payment" → select invoice, enter amount → submit | Payment recorded, invoice status updated | P0 - Critical | Not Tested
TC-011 | Payments | Web | Process refund | Select payment → click "Refund" → enter amount → confirm | Refund processed, payment marked refunded | P1 - High | Not Tested
TC-012 | Payments | Web | Reconciliation | Compare recorded vs. bank payments | Discrepancies highlighted | P2 - Medium | Not Tested
INSURANCE CLAIMS
TC-013 | Insurance | Web | List insurance claims | Navigate to /clinic/billing-officer-insurance | All claims with provider, patient, status, amounts | P1 - High | Not Tested
TC-014 | Insurance | Web | Submit new claim | Click "New Claim" → fill details → submit | Claim submitted with documentation | P1 - High | Not Tested
TC-015 | Insurance | Web | Track claim adjudication | View claim status changes | Status progression visible: submitted→under_review→approved/rejected | P1 - High | Not Tested
TC-016 | Insurance | Web | Upload supporting documents | Attach documents to a claim | Documents uploaded and linked to claim | P2 - Medium | Not Tested
NOTIFICATIONS
TC-017 | Notifications | Web | Billing notifications | Navigate to /clinic/billing-officer-notifications | Payment alerts, overdue reminders, claim status updates | P2 - Medium | Not Tested

## Accountant
TC # | Module / Page | Platform | Feature / Test Case | Steps to Reproduce | Expected Result | Priority | Status | Tested By | Test Date | Bug ID / Notes
ACCOUNTANT DASHBOARD
TC-001 | Dashboard | Web | Dashboard loads | Login as accountant → /clinic/accountant-dashboard | Shows revenue, expenses, balance, monthly trends, P&L summary | P0 - Critical | Not Tested
INVOICES (READ-ONLY)
TC-002 | Invoices | Web | View invoice list for audit | Navigate to /clinic/accountant-invoices | All invoices with GL coding, reconciliation status | P1 - High | Not Tested
TC-003 | Invoices | Web | Export invoices | Click "Export" → select format (CSV/PDF) | Data exported for accounting software | P1 - High | Not Tested
FINANCIAL REPORTS
TC-004 | Reports | Web | Revenue report | Navigate to /clinic/accountant-reports → Revenue tab | Revenue breakdown by branch, doctor, period | P0 - Critical | Not Tested
TC-005 | Reports | Web | P&L statement | Select P&L report | Profit & Loss with income, expenses, net income | P1 - High | Not Tested
TC-006 | Reports | Web | Cash flow report | Select Cash Flow report | Cash inflows/outflows summary | P2 - Medium | Not Tested
TC-007 | Reports | Web | Tax report | Select Tax report | Tax liability summary for compliance | P2 - Medium | Not Tested
TC-008 | Reports | Web | Audit trail | View financial audit trail | All financial transactions with timestamps, users | P2 - Medium | Not Tested
NOTIFICATIONS
TC-009 | Notifications | Web | Accounting notifications | Navigate to /clinic/accountant-notifications | Month-end alerts, reconciliation reminders | P2 - Medium | Not Tested

## HR Manager
TC # | Module / Page | Platform | Feature / Test Case | Steps to Reproduce | Expected Result | Priority | Status | Tested By | Test Date | Bug ID / Notes
HR DASHBOARD
TC-001 | Dashboard | Web | Dashboard loads | Login as HR → /clinic/hr-dashboard | Staff count, payroll cycle status, attendance, upcoming reviews | P0 - Critical | Not Tested
STAFF DIRECTORY
TC-002 | Staff | Web | View staff directory | Navigate to /clinic/hr-staff | All staff with profiles, documents, department, leave balance | P1 - High | Not Tested
TC-003 | Staff | Web | View staff documents | Click on staff → Documents tab | ID proofs, certificates, etc. visible | P2 - Medium | Not Tested
PAYROLL
TC-004 | Payroll | Web | View salary structures | Navigate to /clinic/hr-payroll → Structures tab | All salary structures with components | P1 - High | Not Tested
TC-005 | Payroll | Web | Generate payslips | Click "Generate Payslips" → select period → confirm | Payslips generated for all staff | P0 - Critical | Not Tested
TC-006 | Payroll | Web | Approve payslip | Click "Approve" on a payslip | Payslip status: generated→approved | P1 - High | Not Tested
TC-007 | Payroll | Web | Mark payslip as paid | Click "Mark Paid" on approved payslip | Payslip marked paid with date | P1 - High | Not Tested
NOTIFICATIONS
TC-008 | Notifications | Web | HR notifications | Navigate to /clinic/hr-notifications | Payroll cycle alerts, document expiry, attendance issues | P2 - Medium | Not Tested

## IT Support
TC # | Module / Page | Platform | Feature / Test Case | Steps to Reproduce | Expected Result | Priority | Status | Tested By | Test Date | Bug ID / Notes
IT DASHBOARD
TC-001 | Dashboard | Web | Dashboard loads | Login as IT → /clinic/it-dashboard | System status, uptime, error logs, user activity | P1 - High | Not Tested
IT SETTINGS
TC-002 | Settings | Web | View system config | Navigate to /clinic/it-settings | Email templates, API keys, backup schedules | P1 - High | Not Tested
INTEGRATIONS
TC-003 | Integrations | Web | View integrations | Navigate to /clinic/it-integrations | SMS, email, payment processor, LIS/PACS configs | P1 - High | Not Tested
TC-004 | Integrations | Web | Test integration connectivity | Click "Test Connection" on an integration | Test result shows success/failure | P2 - Medium | Not Tested
NOTIFICATIONS
TC-005 | Notifications | Web | IT notifications | Navigate to /clinic/it-notifications | System alerts, error notifications, integration failures | P2 - Medium | Not Tested

## Support Staff
TC # | Module / Page | Platform | Feature / Test Case | Steps to Reproduce | Expected Result | Priority | Status | Tested By | Test Date | Bug ID / Notes
SUPPORT DASHBOARD
TC-001 | Dashboard | Web | Dashboard loads | Login as support → /clinic/support-dashboard | Stats, care reminders, patient follow-ups, activity log | P0 - Critical | Not Tested
APPOINTMENTS
TC-002 | Appointments | Web | View appointments | Navigate to /clinic/support-appointments | Appointment list with reminder tracking, attendance confirmations | P1 - High | Not Tested
NOTIFICATIONS
TC-003 | Notifications | Web | Support notifications | Navigate to /clinic/support-notifications | Reminders, urgent alerts, follow-up notifications | P2 - Medium | Not Tested

## Patient (Web)
TC # | Module / Page | Platform | Feature / Test Case | Steps to Reproduce | Expected Result | Priority | Status | Tested By | Test Date | Bug ID / Notes
PATIENT LOGIN & AUTH
TC-001 | Login | Web | Patient login page loads | Navigate to /patient/login | Login form with email, password, clinic code entry | P0 - Critical | Not Tested
TC-002 | Login | Web | Login with valid credentials | Enter patient email + password → submit | Successfully logged in, redirected to dashboard | P0 - Critical | Not Tested
TC-003 | Login | Web | Login with wrong password | Enter wrong password → submit | Error message shown, no login | P0 - Critical | Not Tested
TC-004 | Login | Web | Patient logout redirects correctly | Click logout | Redirected to /patient/login (NOT /clinic/login) | P0 - Critical | Not Tested
PATIENT DASHBOARD
TC-005 | Dashboard | Web | Dashboard loads | Login as patient → /patient | Greeting, upcoming appointments, care reminders, quick booking CTA | P0 - Critical | Not Tested
TC-006 | Dashboard | Web | Upcoming appointment card | View dashboard → appointment section | Shows next appointment with doctor, time, join button for teleconsult | P1 - High | Not Tested
TC-007 | Dashboard | Web | Care reminder alerts | View dashboard → care section | Active care reminders shown with due times | P1 - High | Not Tested
APPOINTMENTS
TC-008 | Appointments | Web | List own appointments | Navigate to /patient/appointments | Shows all patient appointments (upcoming + past) | P0 - Critical | Not Tested
TC-009 | Appointments | Web | Book new appointment | Click "Book Appointment" → select department, doctor, time → confirm | Appointment booked with status=requested | P0 - Critical | Not Tested
TC-010 | Appointments | Web | View appointment details | Click on an appointment | Full details: doctor, time, status, notes, join telemedicine button | P1 - High | Not Tested
TC-011 | Appointments | Web | Cancel appointment | Click "Cancel" on an appointment | Appointment cancelled | P1 - High | Not Tested
TC-012 | Appointments | Web | Reschedule appointment | Click "Reschedule" → pick new time → confirm | Appointment rescheduled to new time | P1 - High | Not Tested
TC-013 | Appointments | Web | Confirm attendance (from reminder) | Click "Confirm" on attendance prompt | Attendance confirmed, notification to clinic | P1 - High | Not Tested
TC-014 | Appointments | Web | Check-in via portal | Click "Check In" on confirmed appointment | Status: confirmed→checked_in | P2 - Medium | Not Tested
HEALTH / PRESCRIPTIONS
TC-015 | Health | Web | View prescriptions list | Navigate to /patient/health → Prescriptions tab | All prescriptions with doctor, date, status | P1 - High | Not Tested
TC-016 | Health | Web | View medical records | Navigate to /patient/health → Records tab | Treatment records, diagnoses, test results | P1 - High | Not Tested
BILLING & PAYMENTS
TC-017 | Payments | Web | View invoices | Navigate to /patient/payments | Outstanding and paid invoices with amounts, dates | P0 - Critical | Not Tested
TC-018 | Payments | Web | Make online payment | Click "Pay" on an invoice → complete payment | Payment processed via Razorpay, invoice updated | P0 - Critical | Not Tested
TC-019 | Payments | Web | Download invoice PDF | Click "Download PDF" | PDF invoice downloaded | P2 - Medium | Not Tested
TC-020 | Payments | Web | View payment history | Check transaction history section | All past payments with receipts | P2 - Medium | Not Tested
PROFILE & SETTINGS
TC-021 | Profile | Web | View own profile | Navigate to /patient/profile | Name, email, phone, emergency contact | P1 - High | Not Tested
TC-022 | Profile | Web | Edit profile | Click "Edit" → change details → save | Profile updated | P1 - High | Not Tested
EMERGENCY
TC-023 | Emergency | Web | Send emergency request | Navigate to /patient/emergency → click "Send Emergency" | Emergency session created, doctors notified | P0 - Critical | Not Tested
VIDEO CONSULTATION
TC-024 | Video | Web | Join telemedicine call | Click "Join" on a teleconsult appointment | Video call interface with WebRTC stream | P0 - Critical | Not Tested
TC-025 | Video | Web | In-call chat | During video → send message | Message delivered to doctor | P1 - High | Not Tested
SHARE RECORDS
TC-026 | Share | Web | Generate share link | Navigate to /patient/share-records → create share | Share token generated with expiry date | P1 - High | Not Tested
TC-027 | Share | Web | Access shared record (public URL) | Open /shared/:token in incognito | Medical record visible without login | P1 - High | Not Tested
TC-028 | Share | Web | Revoke share token | Click "Revoke" on a share token | Token invalidated, link no longer works | P2 - Medium | Not Tested
CONSENTS
TC-029 | Consents | Web | View consent forms | Navigate to /patient/consents | Treatment and data-sharing consent forms | P1 - High | Not Tested
TC-030 | Consents | Web | Approve consent | Click "Approve" on a consent form | Consent approved with timestamp | P1 - High | Not Tested
TC-031 | Consents | Web | Revoke consent | Click "Revoke" on an approved consent | Consent revoked | P2 - Medium | Not Tested
ACTIVITY LOG
TC-032 | Activity | Web | View access log | Navigate to /patient/activity-log | Shows who accessed records, when, for what purpose | P1 - High | Not Tested
TC-033 | Activity | Web | Staff access appears in log | After a doctor views patient profile → check activity log | Doctor's access logged with timestamp, accessType=view | P1 - High | Not Tested
DEPENDENTS (GUARDIAN)
TC-034 | Dependents | Web | List dependents | Navigate to /patient/dependents | Shows child/elderly dependent profiles | P1 - High | Not Tested
TC-035 | Dependents | Web | Add dependent | Click "Add Dependent" → fill form → submit | Dependent created and visible in list | P1 - High | Not Tested
TC-036 | Dependents | Web | Switch to dependent profile | Click on dependent → switch context | Dashboard shows dependent's data | P1 - High | Not Tested
REVIEWS
TC-037 | Reviews | Web | Submit doctor review | Navigate to /patient/reviews → write review → submit | Review submitted with star rating | P2 - Medium | Not Tested
NOTIFICATIONS
TC-038 | Notifications | Web | View notification inbox | Navigate to /patient/notifications | All patient notifications by type | P1 - High | Not Tested

## Patient (Mobile)
TC # | Module / Page | Platform | Feature / Test Case | Steps to Reproduce | Expected Result | Priority | Status | Tested By | Test Date | Bug ID / Notes
HOME TAB — DASHBOARD
TC-001 | Dashboard | Mobile | Dashboard loads with clinic info | Open app → Home tab | Shows clinic name, profile switcher, upcoming appointments | P0 - Critical | Not Tested
TC-002 | Dashboard | Mobile | Stats cards render | Scroll dashboard | Financial summary, treatment timeline, appointment count | P1 - High | Not Tested
TC-003 | Dashboard | Mobile | Care reminder alerts | Check care section on dashboard | Active reminders with due times | P1 - High | Not Tested
TC-004 | Dashboard | Mobile | Profile switcher (guardian) | Tap profile switcher → select dependent | Dashboard refreshes with dependent's data | P1 - High | Not Tested
TC-005 | Notifications | Mobile | Open notification list | Tap notification bell icon | All notifications with read/unread indicators | P1 - High | Not Tested
TC-006 | Notifications | Mobile | Mark all as read | Tap "Mark all as read" | All notifications marked read, badge cleared | P2 - Medium | Not Tested
APPOINTMENTS TAB
TC-007 | Appointments | Mobile | List appointments | Tap Appointments tab | All appointments with status badges, doctor info, time | P0 - Critical | Not Tested
TC-008 | Appointments | Mobile | Filter by status (Upcoming/Completed/Cancelled) | Tap filter chips | List filtered correctly | P1 - High | Not Tested
TC-009 | Appointments | Mobile | View appointment detail | Tap on an appointment | Full detail: doctor, clinic, time, status, actions | P0 - Critical | Not Tested
TC-010 | Appointments | Mobile | Book new appointment | Tap "Book" → select clinic/dept/doctor/time → confirm | Appointment booked successfully | P0 - Critical | Not Tested
TC-011 | Appointments | Mobile | Cancel appointment | Tap "Cancel" on appointment detail | Appointment cancelled | P1 - High | Not Tested
TC-012 | Appointments | Mobile | Join telemedicine from appointment | Tap "Join Call" on teleconsult appointment | Video call screen opens | P0 - Critical | Not Tested
HEALTH TAB — MEDICAL RECORDS
TC-013 | Medical History | Mobile | View medical history | Tap Health tab → Medical History | Past treatments, diagnoses, allergies | P1 - High | Not Tested
TC-014 | Prescriptions | Mobile | List prescriptions | Tap Health tab → Prescriptions | Active and past prescriptions | P1 - High | Not Tested
TC-015 | Prescriptions | Mobile | View prescription detail | Tap on a prescription | Medicine names, dosage, frequency, refill status | P1 - High | Not Tested
TC-016 | Share Records | Mobile | Share medical records | Tap "Share Records" | Generate share link with expiry, audit log | P2 - Medium | Not Tested
HEALTH TAB — DENTAL SCANS
TC-017 | Dental Scans | Mobile | View scan history | Navigate to Health → Dental Scans | List of previous scans with dates, status | P1 - High | Not Tested
TC-018 | Dental Scans | Mobile | Start dental scan capture | Tap "New Scan" → grant camera permissions | Camera opens with multi-position guide (6 angles) | P0 - Critical | Not Tested
TC-019 | Dental Scans | Mobile | Capture all 6 angles | Follow voice guidance → capture each angle | All positions captured, preview shown | P0 - Critical | Not Tested
TC-020 | Dental Scans | Mobile | Submit scan for AI analysis | After capture → tap "Analyze" | Scan submitted, loading indicator shown | P0 - Critical | Not Tested
TC-021 | Dental Scans | Mobile | View AI analysis results | After analysis complete → view results | 3D tooth visualization, AI findings, recommendations | P0 - Critical | Not Tested
TC-022 | Dental Scans | Mobile | Export scan result to PDF | Tap "Export PDF" | PDF generated and shareable | P2 - Medium | Not Tested
HEALTH TAB — CARE TASKS
TC-023 | Care Tasks | Mobile | List care tasks | Navigate to Health → Care Tasks | Medication reminders, follow-ups, post-treatment care | P1 - High | Not Tested
TC-024 | Care Tasks | Mobile | View task detail | Tap on a care task | Task details, reminder schedule, completion history | P1 - High | Not Tested
TC-025 | Care Tasks | Mobile | Mark task as done | Tap "Done" on a care task | Task marked complete, logged | P1 - High | Not Tested
TC-026 | Care Tasks | Mobile | Skip task | Tap "Skip" on a care task | Task skipped for this occurrence | P2 - Medium | Not Tested
PAYMENTS TAB
TC-027 | Payments | Mobile | View payment list | Tap Payments tab | Pending and paid invoices with amounts | P0 - Critical | Not Tested
TC-028 | Payments | Mobile | View financial summary | Navigate to financial summary screen | Lifetime spending, category breakdown, outstanding balance | P1 - High | Not Tested
MORE TAB — PROFILE
TC-029 | Profile | Mobile | View own profile | Tap More → Profile | Avatar, name, email, phone, clinic code | P1 - High | Not Tested
TC-030 | Profile | Mobile | Edit profile | Tap "Edit" → change name/phone → save | Profile updated | P1 - High | Not Tested
MORE TAB — DEPENDENTS
TC-031 | Dependents | Mobile | List dependents | Tap More → Dependents | Family members with relationship type | P1 - High | Not Tested
TC-032 | Dependents | Mobile | Add dependent | Tap "Add" → fill form → submit | Dependent created | P1 - High | Not Tested
TC-033 | Dependents | Mobile | Edit dependent | Tap dependent → edit → save | Dependent info updated | P2 - Medium | Not Tested
TC-034 | Dependents | Mobile | View dependent compliance | Tap dependent → compliance tab | Care adherence metrics for dependent | P2 - Medium | Not Tested
MORE TAB — CONSENTS & ACCESS LOG
TC-035 | Consents | Mobile | View consent forms | Tap More → Consents | Treatment and data sharing consents | P1 - High | Not Tested
TC-036 | Access Log | Mobile | View access log | Tap More → Access Log | Who viewed records, when, access type | P1 - High | Not Tested
TC-037 | Access Log | Mobile | View access log detail | Tap on an entry | Full detail: accessor, timestamp, resource, description | P2 - Medium | Not Tested
MORE TAB — SETTINGS & OTHER
TC-038 | Settings | Mobile | App settings | Tap More → Settings | Notification preferences, language, theme | P2 - Medium | Not Tested
TC-039 | Reviews | Mobile | Submit review | Tap More → Reviews → write review | Review submitted with star rating | P2 - Medium | Not Tested
TC-040 | Policy | Mobile | View legal policies | Tap More → Policy | T&C and privacy policy displayed | P3 - Low | Not Tested
EMERGENCY
TC-041 | Emergency | Mobile | Emergency triage form | Trigger emergency → fill triage form | Symptom intake, severity, location confirmed | P0 - Critical | Not Tested
TC-042 | Emergency | Mobile | Emergency session created | Submit emergency request | Session created, doctors notified via socket + FCM | P0 - Critical | Not Tested
VIDEO CALLS
TC-043 | Video Call | Mobile | Receive incoming call | Doctor initiates call → patient gets notification | Full-screen incoming call modal with accept/decline | P0 - Critical | Not Tested
TC-044 | Video Call | Mobile | Accept and join video call | Tap "Accept" on incoming call | WebRTC video stream established | P0 - Critical | Not Tested
TC-045 | Video Call | Mobile | In-call controls (mute, speaker, end) | During call → test audio controls | Mute/unmute, speaker toggle, end call all work | P0 - Critical | Not Tested
TC-046 | Video Call | Mobile | In-call chat messaging | During call → open chat → send message | Message delivered to other participant | P1 - High | Not Tested

## Doctor (Mobile)
TC # | Module / Page | Platform | Feature / Test Case | Steps to Reproduce | Expected Result | Priority | Status | Tested By | Test Date | Bug ID / Notes
HOME TAB — DASHBOARD
TC-001 | Dashboard | Mobile | Dashboard loads with stats | Open app as doctor → Home tab | Greeting, stats (patients, appointments, revenue), current room | P0 - Critical | Not Tested
TC-002 | Dashboard | Mobile | Presence toggle | Toggle online/offline presence | Presence status updated, visible to receptionists | P0 - Critical | Not Tested
TC-003 | Dashboard | Mobile | Today's schedule timeline | View schedule section on dashboard | Timeline of today's appointments | P1 - High | Not Tested
TC-004 | Dashboard | Mobile | Emergency alert notification | When emergency request comes in | Alert badge appears on dashboard | P0 - Critical | Not Tested
TC-005 | Room Monitor | Mobile | View room occupancy | Tap room monitor from dashboard | Real-time room status with patient queue | P2 - Medium | Not Tested
SCHEDULE TAB — APPOINTMENTS
TC-006 | Schedule | Mobile | View weekly schedule | Tap Schedule tab | Weekly view with appointment slots | P0 - Critical | Not Tested
TC-007 | Schedule | Mobile | View appointment detail | Tap on an appointment in schedule | Patient info, chief complaint, actions (check-in, start consultation) | P0 - Critical | Not Tested
TC-008 | Schedule Mgmt | Mobile | Configure availability | Navigate to Schedule Management | Set working hours, break times, block slots | P1 - High | Not Tested
SCHEDULE TAB — CONSULTATIONS
TC-009 | Consultation | Mobile | Start consultation | Tap "Start Consultation" on checked-in appointment | Consultation screen opens with patient data | P0 - Critical | Not Tested
TC-010 | Consultation | Mobile | Add clinical notes | Enter chief complaint, examination, diagnosis | Notes saved to treatment record | P0 - Critical | Not Tested
TC-011 | Consultation | Mobile | Record vital signs | Enter BP, HR, temp, SpO2 | Vitals recorded on treatment record | P1 - High | Not Tested
TC-012 | Consultation | Mobile | Complete consultation | Tap "Complete" → confirm | Treatment record completed, appointment status→completed | P0 - Critical | Not Tested
SCHEDULE TAB — PRESCRIPTIONS
TC-013 | Prescription | Mobile | Create prescription | During consultation → tap "Prescribe" | Prescription form with medicine selector, dosage, frequency | P0 - Critical | Not Tested
TC-014 | Prescription | Mobile | Submit prescription | Fill prescription → submit | Prescription created and linked to consultation | P0 - Critical | Not Tested
TC-015 | Prescription List | Mobile | View prescriptions list | Navigate to prescription list | All issued prescriptions with patient, date, status | P1 - High | Not Tested
TC-016 | Prescription Detail | Mobile | View prescription detail | Tap on a prescription | Full details: medicines, dosage, refill tracking | P1 - High | Not Tested
SCHEDULE TAB — FOLLOW-UPS & DENTAL
TC-017 | Follow-ups | Mobile | View follow-up list | Navigate to follow-up list | Pending follow-ups with dates, patient info | P1 - High | Not Tested
TC-018 | Dental Review | Mobile | View pending scan reviews | Navigate to dental scan review list | AI-analyzed scans awaiting doctor review | P1 - High | Not Tested
TC-019 | Dental Review | Mobile | Review dental scan | Tap scan → view AI analysis → add notes → submit | Review submitted with doctor findings | P1 - High | Not Tested
TC-020 | Procedures | Mobile | View procedure list | Navigate to procedure list | Completed procedures with details | P2 - Medium | Not Tested
TELEMEDICINE TAB
TC-021 | Teleconsults | Mobile | List scheduled teleconsults | Tap Telemedicine tab | Upcoming video calls with patient info, join buttons | P0 - Critical | Not Tested
TC-022 | Teleconsults | Mobile | Join video call | Tap "Join" on a session | Video call screen opens with WebRTC | P0 - Critical | Not Tested
TC-023 | Emergency Queue | Mobile | View emergency requests | Navigate to Emergency Queue | Pending emergency calls with triage info, priority | P0 - Critical | Not Tested
TC-024 | Emergency Queue | Mobile | Accept emergency request | Tap "Accept" on an emergency | Session accepted, video session created, redirected to call | P0 - Critical | Not Tested
TC-025 | Emergency Queue | Mobile | Decline emergency request | Tap "Decline" on an emergency | Request declined (still available for other doctors) | P1 - High | Not Tested
TC-026 | Chat Inbox | Mobile | View chat inbox | Navigate to chat inbox | Patient chat threads with unread counts | P1 - High | Not Tested
TC-027 | Chat Inbox | Mobile | Send chat message | Tap thread → type message → send | Message delivered to patient | P1 - High | Not Tested
INVENTORY TAB (CONDITIONAL)
TC-028 | Inventory | Mobile | View inventory list | Tap Inventory tab (if visible) | Medical supplies with stock levels | P2 - Medium | Not Tested
TC-029 | Inventory | Mobile | View item detail | Tap on inventory item | Quantity, expiry, reorder info | P2 - Medium | Not Tested
TC-030 | Inventory | Mobile | Request restock | Tap "Restock" → fill form → submit | Restock request created | P2 - Medium | Not Tested
PATIENTS TAB
TC-031 | Patients | Mobile | View patient list | Tap Patients tab | Assigned patients with recent visits | P1 - High | Not Tested
TC-032 | Patients | Mobile | View patient record | Tap on a patient | Complete medical record, allergies, medications | P1 - High | Not Tested
TC-033 | Patients | Mobile | View patient compliance | Tap compliance tab on patient | Care adherence metrics, medication compliance | P2 - Medium | Not Tested
PROFILE TAB
TC-034 | Profile | Mobile | View doctor profile | Tap Profile tab | Avatar, name, specialization, license, bio | P1 - High | Not Tested
TC-035 | Profile | Mobile | Edit profile | Tap "Edit" → update fields → save | Profile updated | P2 - Medium | Not Tested
TC-036 | Settings | Mobile | App settings | Navigate to Settings | Notification prefs, language, theme, logout | P2 - Medium | Not Tested

## Auth & Discovery
TC # | Module / Page | Platform | Feature / Test Case | Steps to Reproduce | Expected Result | Priority | Status | Tested By | Test Date | Bug ID / Notes
WEBSITE — MARKETING / PUBLIC
TC-001 | Home | Web | Landing page loads | Navigate to / | Hero section, features, CTA | P1 - High | Not Tested
TC-002 | Browse | Web | Browse clinics page | Navigate to /browse | Clinic cards with search by location/specialty | P1 - High | Not Tested
TC-003 | Clinic Profile | Web | Public clinic profile | Navigate to /clinics/:slug | Clinic info, departments, doctors, reviews | P1 - High | Not Tested
TC-004 | Doctor Profile | Web | Public doctor profile | Navigate to /clinics/:slug/doctors/:id | Qualifications, reviews, book appointment CTA | P1 - High | Not Tested
TC-005 | Features | Web | Features page | Navigate to /features | Product features overview | P3 - Low | Not Tested
TC-006 | Pricing | Web | Pricing page | Navigate to /pricing | Subscription plans for clinics | P2 - Medium | Not Tested
WEBSITE — CLINIC REGISTRATION
TC-007 | Register | Web | Clinic registration wizard | Navigate to /register | Multi-step form: clinic details, plan selection, payment | P0 - Critical | Not Tested
TC-008 | Register | Web | Slug availability check | Enter clinic name → check slug | Slug validated via /public/check-slug/:slug | P1 - High | Not Tested
TC-009 | Register | Web | Paid plan registration with Razorpay | Select paid plan → complete payment | Razorpay order created, payment verified, clinic provisioned | P0 - Critical | Not Tested
TC-010 | Register | Web | Provisioning status polling | After registration → watch progress | Provisioning steps visible: creating_db→seeding→creating_admin→completed | P1 - High | Not Tested
WEBSITE — STAFF LOGIN
TC-011 | Login | Web | Staff login page loads | Navigate to /clinic/login | Email and password fields | P0 - Critical | Not Tested
TC-012 | Login | Web | Valid staff login | Enter staff credentials → submit | Redirected to role-specific dashboard | P0 - Critical | Not Tested
TC-013 | Login | Web | Invalid credentials | Enter wrong password → submit | Error message, no login | P0 - Critical | Not Tested
WEBSITE — PATIENT LOGIN
TC-014 | Login | Web | Patient login page loads | Navigate to /patient/login | Email, password, clinic code entry | P0 - Critical | Not Tested
TC-015 | Login | Web | Valid patient login | Enter patient credentials → submit | Redirected to patient dashboard | P0 - Critical | Not Tested
MOBILE — WELCOME & ONBOARDING
TC-016 | Welcome | Mobile | Welcome screen shows | Open app (first time) | Intro screen with "Get Started" button | P1 - High | Not Tested
TC-017 | Onboarding | Mobile | Onboarding slides | Tap "Get Started" | Feature highlight slides, skip/next buttons | P2 - Medium | Not Tested
MOBILE — CLINIC DISCOVERY
TC-018 | Browse | Mobile | Browse clinics & doctors | Tap "Browse" from welcome | Featured doctors, specializations, geo-search, clinic cards | P1 - High | Not Tested
TC-019 | Clinic Detail | Mobile | View clinic detail | Tap on a clinic | Clinic info, departments, doctors, location, reviews | P1 - High | Not Tested
TC-020 | Doctor Detail | Mobile | View doctor detail | Tap on a doctor | Specializations, qualifications, reviews, booking CTA | P1 - High | Not Tested
TC-021 | Join Clinic | Mobile | Join clinic flow | Tap "Join Clinic" | Search clinics or enter clinic code | P1 - High | Not Tested
TC-022 | Clinic Code | Mobile | Enter clinic code | Tap "Enter Clinic Code" → type JATHR4521 | Clinic resolved, proceed to login/register | P0 - Critical | Not Tested
MOBILE — UNIFIED LOGIN
TC-023 | Login | Mobile | Email lookup step | Enter email in UnifiedLogin | Step 1: Email validated, clinics resolved via /public/lookup-email | P0 - Critical | Not Tested
TC-024 | Login | Mobile | Clinic picker (multi-clinic users) | After email → if multiple clinics found | Step 2: List of clinics to choose from | P0 - Critical | Not Tested
TC-025 | Login | Mobile | Password entry | Select clinic → enter password | Step 3: Login via /public/login with clinicId | P0 - Critical | Not Tested
TC-026 | Login | Mobile | Successful login → navigate to role tab | Complete login flow | Patient → PatientTabNavigator, Doctor → DoctorTabNavigator | P0 - Critical | Not Tested
TC-027 | Login | Mobile | Invalid email shows error | Enter non-existent email | Appropriate error message shown | P1 - High | Not Tested
TC-028 | Login | Mobile | Wrong password shows error | Enter wrong password | Error message, login not successful | P0 - Critical | Not Tested
MOBILE — REGISTRATION
TC-029 | Register | Mobile | Registration screen | Tap "Register" from login | Form: name, email, password, clinic code, terms | P0 - Critical | Not Tested
TC-030 | Register | Mobile | Submit registration | Fill form → submit | Account created, auto-logged in or verify email | P0 - Critical | Not Tested
MOBILE — PASSWORD RESET
TC-031 | Forgot | Mobile | Forgot password flow | Tap "Forgot Password" → enter email | Reset email sent via /public/forgot-password | P1 - High | Not Tested
MOBILE — DENTAL SCAN CHATBOT (PRE-AUTH)
TC-032 | Chatbot | Mobile | Pre-auth dental scan chatbot | Access DentalScanChatbot from auth stack | Guided scan experience without login | P2 - Medium | Not Tested

## Platform Admin
TC # | Module / Page | Platform | Feature / Test Case | Steps to Reproduce | Expected Result | Priority | Status | Tested By | Test Date | Bug ID / Notes
PLATFORM LOGIN
TC-001 | Login | Web | Platform admin login | Navigate to /platform/login | Email/password login for platform admins | P0 - Critical | Not Tested
PLATFORM DASHBOARD
TC-002 | Dashboard | Web | Dashboard loads | Login as platform admin → /platform | Total tenants, revenue, trials, monthly chart, expiring trials | P0 - Critical | Not Tested
TC-003 | Dashboard | Web | Extend trial button | Click "Extend Trial" on an expiring tenant | Trial extended, new expiry date set | P1 - High | Not Tested
TENANT MANAGEMENT
TC-004 | Tenants | Web | List all tenants | Navigate to /platform/tenants | Paginated list with status (active, trial, suspended, cancelled) | P0 - Critical | Not Tested
TC-005 | Tenants | Web | Search tenants | Type in search box | Filtered by clinic name | P1 - High | Not Tested
TC-006 | Tenants | Web | Filter by status | Select status filter | Only matching tenants shown | P1 - High | Not Tested
TC-007 | Tenants | Web | Toggle tenant activation | Click activate/suspend on a tenant | Tenant status toggled, Redis cache invalidated | P0 - Critical | Not Tested
TC-008 | Tenant Detail | Web | View tenant details | Click on a tenant | Clinic info, subscription, staff, usage metrics | P0 - Critical | Not Tested
TC-009 | Tenant Detail | Web | Assign super admin | Click "Assign Super Admin" → select user | Super admin assigned to tenant | P1 - High | Not Tested
TC-010 | Tenant Detail | Web | View audit log | Check audit log section | All tenant admin actions logged | P2 - Medium | Not Tested
PLAN MANAGEMENT
TC-011 | Plans | Web | List subscription plans | Navigate to /platform/plans | All plans with pricing, features, status | P0 - Critical | Not Tested
TC-012 | Plans | Web | Create new plan | Click "Create Plan" → fill form → submit | Plan created with features and pricing | P1 - High | Not Tested
TC-013 | Plans | Web | Edit plan | Click on plan → edit → save | Plan updated | P1 - High | Not Tested
TC-014 | Custom Plan | Web | Custom plan builder | Navigate to /platform/custom-plan-builder | Design bespoke plan for specific tenant | P2 - Medium | Not Tested
SUBSCRIPTIONS
TC-015 | Subscriptions | Web | List all subscriptions | Navigate to /platform/subscriptions | All subscriptions with status, billing dates | P1 - High | Not Tested
TC-016 | Subscriptions | Web | Change tenant plan | Select subscription → change plan | Plan changed with proration | P1 - High | Not Tested
TC-017 | Subscriptions | Web | Cancel subscription | Click cancel on subscription | Subscription cancelled, tenant suspended after grace period | P1 - High | Not Tested
PROMOTIONS & REBATES
TC-018 | Promotions | Web | List promotions | Navigate to /platform/promotions | All promo codes with usage, expiry | P1 - High | Not Tested
TC-019 | Promotions | Web | Create promotion | Click "Create" → fill code, discount, limits → submit | Promotion created | P2 - Medium | Not Tested
TC-020 | Rebates | Web | List rebates | Navigate to /platform/rebates | All rebate programs | P2 - Medium | Not Tested
ANALYTICS
TC-021 | Revenue | Web | Platform revenue analytics | Navigate to /platform/revenue | Revenue by clinic, monthly trends, growth | P1 - High | Not Tested
TC-022 | Subscriptions | Web | Subscription analytics | Navigate to /platform/subscription-analytics | Active count, churn rate, MRR, retention | P1 - High | Not Tested
TC-023 | Platform | Web | Platform analytics | Navigate to /platform/analytics | User growth, feature adoption | P2 - Medium | Not Tested
TC-024 | Dental Scans | Web | Dental scan analytics | Navigate to /platform/dental-scan-analytics | Scans by clinic, accuracy, adoption rate | P2 - Medium | Not Tested
FEATURE FLAGS
TC-025 | Feature Flags | Web | List feature flags | Navigate to /platform/feature-flags | All flags with status, rollout % | P1 - High | Not Tested
TC-026 | Feature Flags | Web | Create feature flag | Click "Create" → name, key, default → submit | Flag created | P2 - Medium | Not Tested
TC-027 | Feature Flags | Web | Set tenant override | Select flag → add tenant override | Override applied for specific tenant | P2 - Medium | Not Tested
PLATFORM USERS
TC-028 | Users | Web | List platform admins | Navigate to /platform/users | All platform admin accounts | P1 - High | Not Tested
TC-029 | Users | Web | Create platform user | Click "Create" → fill form → submit | New platform admin created | P2 - Medium | Not Tested
INTEGRATION & MONITORING
TC-030 | Integrations | Web | Tenant integrations settings | Navigate to /platform/tenants/:slug/integrations | Per-tenant API keys, webhooks, test connectivity | P2 - Medium | Not Tested
TC-031 | Monitoring | Web | System monitoring | Navigate to /platform/monitoring | Health checks, uptime, error dashboard | P2 - Medium | Not Tested

## Push & Real-Time
TC # | Module / Page | Platform | Feature / Test Case | Steps to Reproduce | Expected Result | Priority | Status | Tested By | Test Date | Bug ID / Notes
FCM PUSH NOTIFICATIONS
TC-001 | FCM Setup | Mobile | Device token registration | Login on mobile → check device token saved | POST /auth/register-device succeeds, token in User.fcmTokens[] | P0 - Critical | Not Tested
TC-002 | FCM Setup | Mobile | Token auto-cleanup on invalid | Send push to old token | Invalid token removed from User.fcmTokens[] | P2 - Medium | Not Tested
APPOINTMENT REMINDERS (FCM)
TC-003 | Appt Reminder | Mobile | Appointment reminder push received | Wait for scheduled reminder (15 min scanner) | FCM push notification with appointment details | P0 - Critical | Not Tested
TC-004 | Appt Reminder | Mobile | Yes/No action buttons on notification | Receive appointment reminder → check notification | Notification shows "Confirm" and "Decline" action buttons | P0 - Critical | Not Tested
TC-005 | Appt Reminder | Mobile | Tap "Confirm" action | Tap "Confirm" on notification | Calls portalApi.confirmAttendance(), attendance confirmed | P0 - Critical | Not Tested
TC-006 | Appt Reminder | Mobile | Tap "Decline" action | Tap "Decline" on notification | Attendance declined, clinic notified | P1 - High | Not Tested
TC-007 | Appt Reminder | Mobile | Tap notification body → navigate to appointment | Tap notification body (not action button) | App opens and navigates to appointment detail screen | P1 - High | Not Tested
CARE REMINDERS (FCM)
TC-008 | Care Reminder | Mobile | Care reminder push received | Wait for scheduled care reminder | FCM push with medication/task details | P0 - Critical | Not Tested
TC-009 | Care Reminder | Mobile | Done/Skip action buttons | Receive care reminder notification | "Done" and "Skip" action buttons visible | P1 - High | Not Tested
TC-010 | Care Reminder | Mobile | Tap "Done" action | Tap "Done" on care reminder | Calls portalApi.respondToReminder(), task marked done | P1 - High | Not Tested
TC-011 | Care Reminder | Mobile | Tap "Skip" action | Tap "Skip" on care reminder | Task skipped for this occurrence | P2 - Medium | Not Tested
NOTIFICATION CHANNELS (ANDROID)
TC-012 | Channels | Mobile | Default channel exists | Check Android notification settings for app | Default channel created on app startup | P2 - Medium | Not Tested
TC-013 | Channels | Mobile | Incoming calls channel (ringtone) | Receive incoming call push | Plays ringtone sound, full-screen intent | P0 - Critical | Not Tested
TC-014 | Channels | Mobile | Emergency alerts channel | Receive emergency push | High-priority notification with alert sound | P0 - Critical | Not Tested
TC-015 | Channels | Mobile | Chat messages channel | Receive chat message push | Standard notification with quick-reply action | P1 - High | Not Tested
BACKGROUND / KILLED STATE
TC-016 | Background | Mobile | Notification received while app in background | Put app in background → trigger push | Notification appears in system tray | P0 - Critical | Not Tested
TC-017 | Background | Mobile | Notification received while app killed | Kill app completely → trigger push | Notification appears in system tray | P0 - Critical | Not Tested
TC-018 | Background | Mobile | Tap notification opens correct screen | Tap notification after app was killed | App launches and navigates to relevant screen | P1 - High | Not Tested
SOCKET.IO REAL-TIME
TC-019 | Socket | Both | Socket connects on login | Login on mobile or web → check socket | Socket.io connection established with auth token | P0 - Critical | Not Tested
TC-020 | Socket | Both | Auto-join rooms | Login → verify room membership | Joined: user:{userId}, tenant:{slug}, tenant:{slug}:{role}s | P1 - High | Not Tested
TC-021 | Socket | Both | Emergency request event | Patient sends emergency → check doctor receives | Real-time emergency:new event received by doctors | P0 - Critical | Not Tested
TC-022 | Socket | Both | Presence update event | Doctor toggles presence → check receptionist sees update | presence:update event propagated to tenant room | P1 - High | Not Tested
TC-023 | Socket | Both | Chat message event | Send message in telemedicine chat | chat:message event received by peer in real-time | P1 - High | Not Tested
TC-024 | Socket | Both | Socket reconnects after disconnect | Simulate network drop → restore | Socket auto-reconnects and rejoins rooms | P2 - Medium | Not Tested
TELEMEDICINE / VIDEO CALLS
TC-025 | Video | Both | Initiate video call | Doctor joins telemedicine session | WebRTC peer connection established | P0 - Critical | Not Tested
TC-026 | Video | Both | Patient receives incoming call notification | Doctor joins → patient gets FCM push | Full-screen incoming call modal on mobile | P0 - Critical | Not Tested
TC-027 | Video | Both | Two-way video stream | Both parties in call | Both see each other's video, hear audio | P0 - Critical | Not Tested
TC-028 | Video | Both | Mute/unmute audio | Toggle mute during call | Audio muted/unmuted for remote peer | P1 - High | Not Tested
TC-029 | Video | Both | End call | Tap "End Call" | Call terminated for both parties, session status updated | P0 - Critical | Not Tested
TC-030 | Video | Both | Session chat during video call | Open chat overlay during call → send message | Message visible to other participant | P1 - High | Not Tested
TC-031 | Video | Both | File sharing during session | Upload file during telemedicine session | File uploaded and accessible by both parties | P2 - Medium | Not Tested
TC-032 | Video | Both | Recording consent prompt | When recording is initiated → consent requested | Both parties must consent before recording starts | P2 - Medium | Not Tested
EMAIL NOTIFICATIONS
TC-033 | Email | Backend | Verification email sent on registration | Register new account | Email sent to user (if domain whitelisted) | P1 - High | Not Tested
TC-034 | Email | Backend | Password reset email | Use forgot password flow | Reset link email sent | P1 - High | Not Tested
TC-035 | Email | Backend | Staff invite email | Admin invites new staff member | Invite email with clinic code sent | P1 - High | Not Tested
TC-036 | Email | Backend | Invoice overdue email | Invoice becomes overdue | Overdue notice sent to patient | P2 - Medium | Not Tested
TC-037 | Email | Backend | Dental scan report email | Request email of scan results | Report emailed (domain whitelist checked) | P2 - Medium | Not Tested
TC-038 | Email | Backend | ALLOWED_DOMAINS blocks non-whitelisted | Try sending email to non-whitelisted domain | Email blocked and logged, no delivery | P0 - Critical | Not Tested

## Backend & APIs
TC # | Module / Page | Platform | Feature / Test Case | Steps to Reproduce | Expected Result | Priority | Status | Tested By | Test Date | Bug ID / Notes
AUTHENTICATION & AUTHORIZATION
TC-001 | Auth | Backend | JWT access token generation | POST /auth/login with valid credentials | Returns accessToken + refreshToken | P0 - Critical | Not Tested
TC-002 | Auth | Backend | Token refresh flow | POST /auth/refresh with refreshToken | New accessToken returned | P0 - Critical | Not Tested
TC-003 | Auth | Backend | Expired token rejected | Send request with expired accessToken | 401 Unauthorized returned | P0 - Critical | Not Tested
TC-004 | Auth | Backend | Logout blacklists token | POST /auth/logout | Token blacklisted, subsequent requests rejected | P0 - Critical | Not Tested
TC-005 | Auth | Backend | RBAC permission check (authorize) | Access endpoint requiring APPOINTMENT_CREATE as patient | 403 Forbidden returned | P0 - Critical | Not Tested
TC-006 | Auth | Backend | RBAC permission check (authorizeAny) | Access endpoint requiring APPOINTMENT_READ or APPOINTMENT_READ_OWN | Allowed if user has EITHER permission | P1 - High | Not Tested
TC-007 | Auth | Backend | Rate limiting on login | Send 16 login attempts in 15 minutes | 429 Too Many Requests on 16th attempt | P1 - High | Not Tested
MULTI-TENANT ISOLATION
TC-008 | Tenant | Backend | Tenant resolver extracts slug from header | Send request with x-tenant-id header | Correct tenant database used | P0 - Critical | Not Tested
TC-009 | Tenant | Backend | Missing x-tenant-id header | Send authenticated request without header | Error: tenant header required | P0 - Critical | Not Tested
TC-010 | Tenant | Backend | Cross-tenant data isolation | Login to clinic A → try to access clinic B data | Data from clinic B NOT accessible | P0 - Critical | Not Tested
SUBSCRIPTION ENFORCEMENT
TC-011 | Subscription | Backend | Active subscription allows access | Login to active tenant → make API call | Request succeeds | P0 - Critical | Not Tested
TC-012 | Subscription | Backend | Suspended tenant blocked | Login to suspended tenant → make API call | 403 with { code: "SUBSCRIPTION_BLOCKED", subscriptionStatus, reason } | P0 - Critical | Not Tested
TC-013 | Subscription | Backend | Subscription bypass routes (/auth, /public) | Access /auth/login on suspended tenant | Request succeeds (not blocked) | P0 - Critical | Not Tested
TC-014 | Subscription | Backend | Redis cache invalidation after status change | Suspend tenant → immediately try access | Cache invalidated, new status effective | P1 - High | Not Tested
FEATURE GATING
TC-015 | Features | Backend | Feature guard blocks disabled feature | Access telehealth endpoint on non-telehealth plan | 403: Feature not available | P1 - High | Not Tested
TC-016 | Features | Backend | Feature flag 3-tier resolution | Set global flag ON, plan OFF, tenant override ON → check | Tenant override wins | P1 - High | Not Tested
SOFT DELETE PATTERN
TC-017 | Soft Delete | Backend | Deleted records excluded from queries | Soft-delete a patient → query patients list | Deleted patient NOT in results | P0 - Critical | Not Tested
TC-018 | Soft Delete | Backend | countDocuments includes deletedAt filter | Soft-delete patient → check pagination total | Total count excludes soft-deleted records | P1 - High | Not Tested
PAGINATION & SORTING
TC-019 | Pagination | Backend | Default pagination | GET /patients (no page/limit params) | Returns page 1, default limit (20), total count | P1 - High | Not Tested
TC-020 | Pagination | Backend | MAX_LIMIT enforcement (100) | GET /patients?limit=500 | Returns max 100 items, not 500 | P1 - High | Not Tested
TC-021 | Pagination | Backend | Sort parameter | GET /patients?sort=-createdAt | Results sorted newest first | P2 - Medium | Not Tested
KEY API ENDPOINTS
TC-022 | Appointments API | Backend | GET /appointments with date range | GET /appointments?from=2026-04-01&to=2026-04-30 | Returns appointments within date range | P0 - Critical | Not Tested
TC-023 | Appointments API | Backend | POST /appointments validation | POST /appointments with past date for scheduledAt | Validation error: "Appointment must be in the future" | P1 - High | Not Tested
TC-024 | Patient Portal API | Backend | GET /portal/dashboard/:patientId | Request patient dashboard data | Returns upcoming appointments, care tasks, financial summary | P0 - Critical | Not Tested
TC-025 | Doctor API | Backend | GET /doctor/stats | Request doctor dashboard stats | Returns appointment count, revenue, patients, weekTotal | P1 - High | Not Tested
TC-026 | Billing API | Backend | GET /billing/analytics/revenue?from=X&to=Y | Request billing analytics with date range | Returns { byBranch, monthlyTrend, totals } | P1 - High | Not Tested
TC-027 | Public API | Backend | POST /public/lookup-email | Send { email } to lookup | Returns list of clinics user belongs to | P0 - Critical | Not Tested
TC-028 | Public API | Backend | POST /public/login | Send { clinicId, email, password } | Returns tokens and user data | P0 - Critical | Not Tested
TC-029 | Dental Scan API | Backend | POST /dental-scans/:id/analyze | Submit scan for AI analysis | Returns analysis results with findings | P1 - High | Not Tested
BACKGROUND JOBS (BullMQ)
TC-030 | Jobs | Backend | Appointment reminder scanner runs | Wait for 15-min scan cycle | Due appointment reminders queued for FCM push | P1 - High | Not Tested
TC-031 | Jobs | Backend | Care reminder scanner runs | Wait for care reminder scan cycle | Due care reminders queued for FCM push | P1 - High | Not Tested
TC-032 | Jobs | Backend | Dental scan analysis worker processes | Submit dental scan → check worker | AI analysis completed, result saved | P1 - High | Not Tested
TC-033 | Jobs | Backend | Email worker sends emails | Trigger email action → check delivery | Email sent via SMTP (whitelisted domains only) | P1 - High | Not Tested
TC-034 | Jobs | Backend | Invoice overdue scanner | Create overdue invoice → wait for scan | Overdue notification sent | P2 - Medium | Not Tested
TC-035 | Jobs | Backend | Provisioning worker (multi-step) | Register new clinic | Steps: create_db→generate_code→seed→create_admin→apply_plan→complete | P0 - Critical | Not Tested
TC-036 | Jobs | Backend | Subscription lifecycle worker | Trial expires → check worker | Auto-transitions: trial→grace_period→suspended | P1 - High | Not Tested
TC-037 | Jobs | Backend | Inventory alert worker | Stock falls below reorder point | Low stock notification sent to admin | P2 - Medium | Not Tested
ACCESS LOGGING
TC-038 | Access Log | Backend | Staff view patient profile → logged | Doctor views patient profile via GET /patients/:id | AccessLog entry: accessType=view, resource=profile | P1 - High | Not Tested
TC-039 | Access Log | Backend | Staff create appointment → logged | Staff creates appointment via POST /appointments | AccessLog entry: accessType=create, resource=appointment | P1 - High | Not Tested
TC-040 | Access Log | Backend | Doctor start consultation → logged | Doctor starts consultation | AccessLog entry: accessType=create, resource=treatment | P1 - High | Not Tested
TC-041 | Access Log | Backend | Self-view excluded from log | Patient views own profile | NO AccessLog entry (self-view skip logic) | P1 - High | Not Tested
ERROR HANDLING
TC-042 | Errors | Backend | Validation error format | Send invalid data to any endpoint | Returns { success: false, errors: [...] } with field-level details | P1 - High | Not Tested
TC-043 | Errors | Backend | ApiError with structured data | Trigger subscription block | Returns { code, subscriptionStatus, reason } in error data | P2 - Medium | Not Tested
TC-044 | Errors | Backend | 404 for non-existent resource | GET /patients/nonexistent_id | Returns 404 Not Found | P2 - Medium | Not Tested